## Slide 1: UR Update New Stack Kickoff Meeting
October 29, 2018

## Slide 2: Agenda
Introduction & Stakeholders
Project Scope & Advantages
Current and New Versions
Implementation Approach
Key Milestones
Communication Plan
Q&A / Discussion

## Slide 3: Introduction & Stakeholders
Branch Chief (DPD - IIB) - Jennifer Woodward
Technical Information Specialist (DPD - IIB) - Misha Sogonov
Acquisitions & Metadata Branch Chief (DPD) - Charles Bradsher
Metadata Librarians (DPD) – Emily Somach, Amanda Xu
Digitization (DPD) – Lena Garner, Karen Sichelman
Associate Director (IPD and acting DPD) - Jill James
Collection Development Officer - Michael Esman
Digitization and Access Branch Chief (DPD) - Scott Hanscom
Digital Library Branch Chief (IPD) - Kristina Adams
System Engineers – David Ribeiro, Chris Schoppet
PubAg Technical Team (ISD) – Tuan Nguyen, Kapil Jhamb
System Librarian (ISD) – Ying Li
Automation Developer (ISD) – Chuck Schoppet
Applications Branch Chief (ISD) – Ursula Pieper
Project Manager (ISD) – Sherry Panzer
Associate Director (ISD) – Jeanie Brand
IT Project Manager/Business Analyst (ISD) – Harsha Adusumalli

## Slide 4: Scope & Advantages
Scope:
  To update the components of Islandora stack to the latest versions
Advantages:
  Support increasing number of objects in the repository
    The Mulgara triple is reaching it's limit of triples
    SOLR 4.10 allows for sharing, higher performance and scaling
  Support for more complex SOLR and SPARQL queries for reporting
    The new triple-store supports SPARQL 1.1, adding the NOT function and grouping capability
    SOLR 4.10 adds Pivot Facets
  Increased stability
  Replace/update components that are at end-of-life
GitHub URL: https://github.com/isdapps/pubag-data-management-system/wiki/Differences-between-old-and-new-stacks

## Slide 5: Current and New Versions
Component | Current (old/product) | New
OS | CentOS release 6.10 (Final) | CentOS Linux release 7.5.1804 (Core)
Durpal | Drupal 7.60 | Drupal 7.60
Apache Tomcats | 6.0.35 | 7.0.70
Apache Solr | 3.6.2 | 4.10.4
Database | MySQL Ver 14.14 Distrib 5.5.39 | MariDB Ver 15.1 Distrib 5.5.60
Apache HTTP Server | 2.2.15 | 2.4.6
Islandora | 7.x-1.11 | 7.x-1.11
Fedora Commons | 3.7.1 | 3.8.1(final)
fedora gsearch Solr indexer | 2.6 | 2.8
Apache ActiveMQ | 5.7 | 5.7
Triple-store | [Mulgara][http://mulgara.org/] 2.1.13 (final) | BlazeGraph 2.1.4
 | n/a | Trippi-sail core 1.5.10 Trippi.sail.blazegraph 0.0.1
Hawtio | 1.4.65 | 
ImageMagick | 6.7 | 
Ghostscript | 8.7 | 9.07

## Slide 6: Implementation Approach
Complete Verification, initial Configuration and Notifications
Complete Identification & Documentation
Complete development and integration
Complete Preparation Activities for the move to New Stack
Complete Cutover activities
Complete Move to New Stack
Burn-In Period
UR available for limited use

## Slide 7: Key Milestones
Key Milestone | Completion Date
Verification, Initial Configuration and Notifications | 10/31/2018
Identification & Documentation | 11/6/2018
Development and Integration | 12/10/2018
Preparation Activities | 12/13/2018
Readiness Review | 12/13/2018
Cutover activities | 12/17/2018
Unfreeze repository - Limited Production work begins | 1/3/2019
UR available for limited use | 1/4/2019
Complete Move to New Stack | 2/1/2019
Burn-in Support | 2/15/2019

## Slide 8: Communication Plan
Formal Communication:
  Weekly Status Report & Meetings
Day to Day Communication:
  In-person meeting
  WebEx
  Email
All Escalation will be communicated through formal emails
All Deliverables & Collaboration through SharePoint or GitHub Portal

## Slide 9: Q&A / Discussion